## Family Workplan
Family work plan |  |  |  |  | TODAY'S DATE | 2026-01-23
[5 empty] | Family | X
This helps us track individual task completion and milestones as well as sharing the total rebuilding schedule.
[5 empty] | Work Plan Authorization | 2025-03-20
[9 empty] | 2025-03-01 |  |  |  |  | 2025-04-01 |  |  |  |  | 2025-05-01 |  |  |  |  | 2025-06-02 |  |  |  |  | 2025-07-01 |  |  |  |  | 2025-08-01 |  |  |  |  | 2025-09-01 |  |  |  |  | 2025-10-01 |  |  |  |  | 2025-11-01 |  |  |  |  | 2025-12-01 |  |  |  |  | 2026-01-01 | [5 empty] | 2026-02-01 |  |  |  | 2026-03-02 |  |  |  |  | 2026-04-01 |  |  |  |  | 2026-05-01 |  |  |  |  | 2026-06-01 |  |  |  |  | 2026-07-01 |  |  |  |  | 2026-08-03 |  |  |  |  | 2026-09-01 |  |  |  |  | 2026-10-01 |  |  |  |  | 2026-11-01 |  |  |  |  | 2026-12-01 |  |  |  |  | 2027-01-01 |  |  |  |  | 2027-02-01 |  |  |  |  | 2027-03-01 |  |  |  |  | 2027-04-01 |  |  |  |  | 2027-05-01 |  |  |  |  | 2027-06-01 |  |  |  |  | 2027-07-01 |  |  |  |  | 2027-08-02 |  |  |  |  | 2027-09-01 |  |  |  |  | 2027-10-01 |  |  |  |  | 2027-11-01 |  |  |  |  | 2027-12-01
[9 empty] | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-01 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-03-31 | 2025-05-01 | 2025-05-05 | 2025-05-12 | 2025-05-12 | 2025-05-19 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-01 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-01 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-01 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-01 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-01 | 2026-01-05 | 2026-01-12 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-01 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-01 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-01 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-01 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-01 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-01 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-02-28 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-01 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-01 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-01 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-01 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27 | 2027-10-01 | 2027-10-04 | 2027-10-11 | 2027-10-18 | 2027-10-25 | 2027-11-01 | 2027-11-08 | 2027-11-15 | 2027-11-22 | 2027-11-29 | 2027-12-01 | 2027-12-06 | 2027-12-13 | 2027-12-20 | 2027-12-27
| ✓ | TASK | PRIORITY | STATUS |  | START | END | DUR
| FALSE |  | Med |  | Complete | 2025-02-28 | 2025-03-04 | 5
| FALSE |  | Med |  | In Progress | 2025-02-28 | 2025-03-04 | 5
| FALSE |  | High |  | Not Started | 2025-02-28 | 2025-03-04 | 5
| FALSE |  | High |  | Not Started | 2025-02-28 | 2025-03-04 | 5
FALSE
FALSE
0%
2 |  | Feasibility & Conceptual Development
2.01 | FALSE | Develop work plan & draft budget |  |  | Not Started
2.02 | FALSE | Send program survey |  |  | Not Started
2.03 | FALSE | Finalize work plan and budget |  |  | Not Started
2.04 | FALSE | Complete zoning and site review |  |  | Not Started
2.05 | FALSE | Develop 3-4 fit tests |  |  | Not Started
2.06 | FALSE | Confirm Insurance payouts |  |  | Not Started
2.07 | FALSE | Revise per cost scenarios |  |  | Not Started
2.08 | FALSE | Define project vision and goals |  |  | Not Started
2.09 | FALSE | Spatial layouts |  |  | Not Started
2.1 | FALSE | Define aesthetic and special design features |  |  | Not Started
2.11 | FALSE |  |  |  | Not Started
2.12 | FALSE
2.13 | FALSE
2.14 | FALSE
2.15 | 0%
3 |  | Design Development
3.01 | FALSE | Massing and roofline strategies |  |  | Not Started
3.02 | FALSE | Exterior elevations |  |  | Not Started
3.03 | FALSE | Interior floor plans |  |  | Not Started
3.04 | FALSE | Renderings and visualizations |  |  | Not Started
3.05 | FALSE | Structural engineer review for feasibility |  |  | Not Started
3.06 | FALSE | Draft project cost estimate |  |  | Not Started
3.07 | FALSE | Finalize comprehensive design package |  |  | Not Started
3.08 | FALSE
3.09 | FALSE
3.1 | FALSE
3.11 | FALSE
3.12 | FALSE
3.13 | FALSE
3.14 | FALSE
3.15 | FALSE
0%
4 |  | (Optional) Alternative Funding Models
4.01 | FALSE | Loans and financing options |  |  | Not Started
4.02 | FALSE | Access new funding sources |  |  | Not Started
4.03 | FALSE | Lot splits, tenancy in common, etc. |  |  | Not Started
4.04 | FALSE | Community ownership models |  |  | Not Started
4.05 | FALSE | Referral to Greenline Housing Foundation |  |  | Not Started
4.06 | FALSE | Homeowner financial planning including O&M |  |  | Not Started
4.07 | FALSE
4.08 | FALSE
4.09 | FALSE
4.1 | FALSE
4.11 | FALSE
4.12 | FALSE
4.13 | FALSE
4.14 | FALSE
4.15 | FALSE
0%
5 |  | Bidding
5.01 | FALSE | Develop bidding criteria & list |  |  | Not Started
5.02 | FALSE | Coordinate bids |  |  | Not Started
5.03 | FALSE | Review, clarifications, & amendments |  |  | Not Started
5.04 | FALSE | Recommendations |  |  | Not Started
5.05 | FALSE
5.06 | FALSE
5.07 | FALSE
5.08 | FALSE
5.09 | FALSE
5.1 | FALSE
5.11 | FALSE
5.12 | FALSE
5.13 | FALSE
5.14 | FALSE
5.15 | FALSE
0%
6 |  | Engineering, Architecture, MEP
6.01 | FALSE | Develop Architectural Permitting Plans |  |  | Not Started
6.02 | FALSE | Coordinate with Structural Engineer |  |  | Not Started
6.03 | FALSE | Structural Engineer set of drawings development |  |  | Not Started
6.04 | FALSE | Mechanical plans developed as needed |  |  | Not Started
6.05 | FALSE | Specs and appliances |  |  | Not Started
6.06 | FALSE
6.07 | FALSE
6.08 | FALSE
6.09 | FALSE
6.1 | FALSE
6.11 | FALSE
6.12 | FALSE
6.13 | FALSE
6.14 | FALSE
6.15 | FALSE
0%
7 |  | Permitting
7.01 | FALSE | Submit permit set to building & safety - expedited |  |  | Not Started
7.02 | FALSE | Review corrections |  |  | Not Started
7.03 | FALSE | Obtain clearances |  |  | Not Started
7.04 | FALSE | Obtain RTI |  |  | Not Started
7.05 | FALSE
7.06 | FALSE
7.07 | FALSE
7.08 | FALSE
7.09 | FALSE
7.1 | FALSE
7.11 | FALSE
7.12 | FALSE
7.13 | FALSE
7.14 | FALSE
7.15 | FALSE
0%
8 |  | Construction
8.01 | FALSE | Coordinate construction schedule |  |  | Not Started
8.02 | FALSE | On-site progress meetings |  |  | Not Started
8.03 | FALSE | Manage change orders & budget |  |  | Not Started
8.04 | FALSE | Monitor inspector visits |  |  | Not Started
8.05 | FALSE | Authorize construction draws |  |  | Not Started
8.06 | FALSE | Punchlist closing out construction |  |  | Not Started
8.07 | FALSE | Obtain Certificate of Occupancy |  |  | Not Started
8.08 | FALSE
8.09 | FALSE
8.1 | FALSE
8.11 | FALSE
8.12 | FALSE
8.13 | FALSE
8.14 | FALSE
8.15 | FALSE
0%
9 |  | Move In!
9.01 | FALSE
9.02 | FALSE
9.03 | FALSE
9.04 | FALSE
9.05 | FALSE
9.06 | FALSE
9.07 | FALSE
9.08 | FALSE
9.09 | FALSE
9.1 | FALSE
9.11 | FALSE
9.12 | FALSE
9.13 | FALSE
9.14 | FALSE
9.15 | FALSE
0%
10 |  | Milestone 10
10.01 | FALSE
10.02 | FALSE
10.03 | FALSE
10.04 | FALSE
10.05 | FALSE
10.06 | FALSE
10.07 | FALSE
10.08 | FALSE
10.09 | FALSE
10.1 | FALSE
10.11 | FALSE
10.12 | FALSE
10.13 | FALSE
10.14 | FALSE
10.15 | FALSE
0%

## Budget
FUNDS & COSTS | [6 empty] | RESOURCES RECIEVED |  |  |  |  | SURPLUS / DEFICIT |  |  |  | PENDING OR WITHHELD
[9 empty] | 972000 |  |  |  |  | -349800 |  |  | 111000
- Homeowner Overview -
P E R I O D S E L E C T I O N
F R O M : |  |  | 2025-02-28
T O : |  |  | 2027-06-30
% OF NEEDED RESOURCES SECURED
73.54%
|  |  |  | RESOURCES | [8 empty] | ESTIMATED COSTS
TOTAL COST TO REBUILD
|  |  |  | C A T E G O R I E S | RECEIVED |  |  | LINE ITEM |  | WITHHELD |  |  | C A T E G O R I E S |  | T Y P E |  |  | T O T A L
|  | 1321800 |  | Insurance - Primary Structure |  | 550000 |  |  | 558000 |  | 8000 |  | Construction Cost |  | 600 |  |  |  | 1200000
|  |  |  | Insurance - Additional Structures |  | 100000 |  |  | 100000 |  | 0 |  | Construction Contingency |  | 7% |  |  |  | 84000
|  |  |  | Insurance - Personal Property |  | 2000 |  |  | 75000 |  | 73000 |  | Permitting Plans | [5 empty] | 25000
|  |  |  | Insurance - Loss of Use |  | 125000 |  |  | 125000 |  | 0 |  | LID Review | [5 empty] | 800
| TOTAL SQ.FT. |  |  | Insurance - Extended Dwelling |  | 10000 |  |  | 10000 |  | 0 |  | Structural Set | [5 empty] | 12000
|  |  |  | Loan - HELOC |  | 50000 |  |  | 50000 |  | 0 |  | Architectural Permit Seet | [5 empty] | 144000
|  | 2000 |  | FEMA Assistance |  | 125000 |  |  | 125000 |  | 0 |  | TOTAL COST | [5 empty] | 1321800
|  |  |  | Edison Settlement |  | 0 |  |  | 0 |  | 0
|  |  |  | Misc. Funds |  | 10000 |  |  | 40000 |  | 30000
Direct Cost
| TOTAL HARD COSTS |  |  | T O T A L |  | 972000 |  |  | 1083000 |  | 111000
1321800
Operating Cost
TOTAL SOFT COSTS
265800